Project Update April 10th

Over the past week, the team has made significant progress in both the predictive and causal modeling components of the project, building directly on the foundation established prior to Spring Break.

Predictive Modeling (Marco & Marisa):

Marco and Marisa successfully completed hyperparameter optimization for the XGBoost predictive model. This included systematic tuning of key parameters such as learning rate, max depth, number of estimators, and subsampling ratios using cross-validation on the PACE environment. As a result, the model has maintained strong performance, with AUROC remaining in a high-performing range while improving generalizability across folds.

In addition to hyperparameter tuning, they have begun refining model performance beyond AUROC by focusing on precision-recall tradeoffs, which are especially important given the class imbalance in ICU admission and mortality outcomes. They are actively experimenting with decision threshold tuning to optimize recall (sensitivity) without excessively sacrificing precision, depending on the clinical objective. For example, lower thresholds are being evaluated to better capture high-risk patients (minimizing false negatives), while alternative thresholds are being tested to reduce false positives in resource-limited ICU settings.

They are also working on generating heatmaps and feature importance visualizations to better interpret model outputs. This includes SHAP-based analyses to identify which clinical features and KATE score components are most influential in predicting ICU admission or death. These visualizations will support both model validation and downstream causal analysis.

Causal Modeling (Ashwith & Samuel, with Jonathan):

On the causal inference side, Ashwith and Samuel have expanded beyond initial testing with DoWhy and are now actively implementing the EconML library, which provides more advanced estimators for heterogeneous treatment effects.

They successfully implemented a T-learner framework on a subset of the dataset. This approach involves training separate models for treated (high KATE risk) and control (low KATE risk) groups to estimate conditional treatment effects. Initial runs have demonstrated that the pipeline is functional, though further work is needed to ensure proper covariate balance and robustness.

A major current focus is determining how to integrate the predictive model outputs into the causal framework. Specifically, they are exploring:

- Using predicted risk scores as inputs or stratification variables in the causal model

- Defining treatment as “high-risk by KATE” and outcome as ICU admission or death

- Identifying and adjusting for confounders (e.g., demographics, comorbidities, baseline severity metrics)

They are also working through challenges related to:

- Proper treatment assignment definition (binary vs continuous risk thresholds)

- Ensuring overlap/positivity assumptions hold across risk groups

- Feature engineering to align predictive and causal datasets

In parallel, Ashwith and Samuel are continuing a literature review on causal inference methods, comparing approaches such as T-learners, S-learners, doubly robust learners, and instrumental variable methods to determine the most appropriate framework for this clinical question.

Jonathan has now officially joined this subgroup and is contributing to both the predictive-causal integration and debugging efforts. While there were initial issues adding him to the GitHub repository, coordination is ongoing and he is actively collaborating on model development and testing.