Project Update April 3rd

Marisa finished the initial dataset for both predictive and causal models based on feedback from prior to Spring Break. The decision was made to use only the subset of the DiReCT Notes Extension that had matching sample identifiers. Marco created the predictive model using XGBoost and tested it on a small subset locally on his computer. He created the framework for modeling precision recall as well. Marisa and Marco worked to test it on PACE using the full dataset which is currently showing an AUROC of 0.8652. In the next week, Marisa and Marco plan to work on hyper parameter tuning and to develop a heat map of the results.

Samuel found a DoWhy causal library and implemented it on a test dataset to see if it is possible to implement it to our project dataset. Samuel and Ashwith are working this week to better understand the library and how to use it for dataset. Both are doing a lit review of causal reasoning models to find additional libraries or code that can be used. They plan to implement causal reasoning using the outputs of the predictive model to determine causal relationships between features, treatment, and outcome in the next few weeks.